## Sheet1
Title： | Total points |  | 50 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Actual Velocity
App Interface Prototype | 3 | DONE | 50: 1; 1: 0 | 0
User Registration & Login | 4 | DONE | 50: 2; 2: 3 | 3
Booking a Cleaning Service | 4 | DONE | 50: 3; 3: 9 | 9
Viewing Available Time Slots | 3 | DONE | 50: 4; 4: 1 | 1
Cleaner Profile and Rating System | 2 | DONE | 50: 5; 5: 4 | 4
Real-Time Chat with Cleaners | 3 | DONE | 50: 6; 6: 7 | 7
Booking Status Notification | 3 | DONE | 50: 7; 7: 8
Payment Integration | 4 | DONE | 50: 8; 8: 6
Rebooking and Service History | 2 | DONE | 50: 9; 9: 2
Cleaner Availability Management | 2 | X | 50: 10; 10: 1
Admin Dashboard & Monitoring | 3 | X
Review and Rating Submission | 2 | DONE
Feedback System for App Improvement | 1 | DONE
Push Notification for Booking Reminder | 2 | DONE
Emergency Cancellation Option | 3 | DONE
Multilingual Support | 1 | DONE
Cleaner Verification Process | 4 | DONE
Promotional Offers and Discount Codes | 2 | DONE
Location-based Booking Suggestions | 2 | DONE
50